## COST SHARE INFO
So You Got A State Cost Share Approved - Now What?
Below are some steps to follow after the conservation district has received notification from the Division of Conservation that State Cost Share (SCS) applications
from your county have been approved. This list is not exhaustive and if you have any questions regarding the SCS process, please contact your field representative.
After an Application is Approved
The conservation district needs to notify all applicants of the approval or denial of their application. This should include any additional information pertaining to their
project, like if they need to take soil samples, etc.
After notifying the applicant, the district needs to update their monthly SCS report with the new approvals and any internal tracking sheets.
Districts are also responsible for notifying any partner agencies that provide technical assistance that applicants are approved or denied.
The district will then work with their technical assistance provider to complete plans, engineering designs, and other such materials for the landowner. The district should
retain records on site of all documents relating to a SCS contract, including the application, an Ag Water Quality Plan, designs, maps, and other such materials.
The district will then assist in scheduling follow-up field visits to complete tasks such as engineering designs and ensure that the landowner understands and can implement their SCS.
Districts should insure that landowners have electronic or paper copies of their Ag Water Quality plan, designs, maps, and other documents.
The district should ask the landowner to contact the technical assistance provider or the conservation district once they are ready to commence practices.
After 6 months have passed from the initial approval, the district should reach out to the landowner either via mail, email or phone call to remind them of their project and to see if they
have commenced practices.
30 days prior to the end of the 1st contract year, the district should reach out to the landowner to see if they would like an extension.
Extension requests need to be written by the landowner. When requesting extension requests for multiple participants please include all the names on the state cost share extension
request form found in the state cost share Excel workbook. Please include the county name, month and year in the spaces provided at the top of the form. Make sure the full practice
ID number (i.e. 20xx-xxx-12345) name of participant, the type of practice (i.e. cropland, livestock-pastureland) and the reason for the extension request. Please include the letters from
the participants requesting the extension in the same email if possible and preferably in pdf file format. Make sure the name is legible and includes the full practice ID number on each letter.
All extension requests need to be sent in to the Division of Conservation (conservation@ky.gov) using the paperwork in the most recent SCS workbook.
If the 1 year mark has passed and the conservation district cannot reach the landowner after multiple attempts, the conservation district can vote to cancel the contract due to no contact.
This should be noted in the meeting minutes.
If the board votes to cancel a contract, the conservation district needs to inform the Division of Conservation by using the cancellation form in the SCS Excel workbook found on the Division of
Conservation website and sent to conservation@ky.gov. When requesting cancellation requests for multiple participants please include all the names on the state cost share cancellation request
form. Please include the county name, month and year in the spaces provided at the top of the form. Make sure the full practice ID number (i.e. 20xx-xxx-12345) name of participant, the type of
practice (i.e. cropland, livestock-pastureland) and the reason for the cancellation request. If the landowner has requested the cancellation, please include the letters from the participant requesting
the cancellation in the same email and preferably in pdf file format. Make sure the name is legible and include the full practice ID number on each letter. If the district cancels the project due to no
response, please include a copy of the meeting minutes with the form.
Update the landowner on approval of extension with new completion due date or of cancellation of contract.
If the landowner will need a second extension, refer to the steps above.
All schedules for extensions and deadlines should be tracked by the conservation district.
All applications must be completed within 2 years. There are no extensions approved beyond 2 years.
Making a Payment
When a landowner has completed a project, they need to contact the conservation district office for a final field visit.
Once the final field visit has been completed, the technical assistance provider needs to certify the practices were implemented correctly.
The landowner needs to provide all bills to the district office. Landowners will be reimbursed for 75% of the bills that are presented. This may be more or less then their estimate at the time of
application, but may not exceed the $20,000 state cost share cap.
The conservation district board should vote to approve the contract for payment.
The conservation district e-mails copies of the bills, the most recent payment form with signatures, the Payment Request Summary Form, and any other documents to Conservation@ky.gov.
All forms can be found in the state cost share Excel workbook. Include the county name, month and year in the spaces provided at the top of the form. Provide the full practice ID number
(i.e. 20xx-xxx-xxxxx), participant's name as it appears on the application (no nicknames or alternate names), the practice ID (i.e. cropland, livestock-pastureland, Animal Feeding Operation).
Include the payment form paperwork with all required signatures signed and all information correctly filled out except for the check number space is to be left blank at this time.
Include the payment summary breakdown page, copies of all of the bills, they must be legible and the participant’s name must be written on each bill. Any items on the bills that do not apply
to the request must be redacted and the totals reconfigured. Show your work!
When scanning, please scan the state cost share payment request form from your workbook first then the payment paperwork and then the bills and preferably in one pdf document emailed
to the Conservation@ky.gov with the subject of “State Cost Share Payment Request” and the County Name.
Wait for the payment request to be confirmed and approved by the Division of Conservation.
Payments will be made directly to the conservation district. Districts are responsible for paying the landowner.
Once payment has been made, you will receive an automated email from the Finance Cabinet letting you know your deposit is on the way. The Division of Conservation will also send out an
approval email showing the amounts we have approved for payment and for whom.
Once you have made the payment, you will include the check number that you issued on your monthly state cost share report reflecting payment of the contract.
Things to Remember
The conservation district needs to maintain records of all SCS applications and contracts at the conservation district office.
The conservation district must submit monthly cost share reports, cancellation requests. extension requests and modification requests on separate workbook pages.
Do not send the entire workbook in for multiple items; example; if you are sending in a cost share report do not also have an extension request in the same workbook, send your extension
request in separately.
Please send in all reports and requests in pdf file format if possible; this will greatly reduce processing time as all documents received are being converted to pdf file format and saved with the
date of receipt; example 02252021-State Cost Share Report-County Name
The conservation district must submit a monthly SCS report.
Be sure to maintain all paid/cancelled/expired contracts on your monthly cost share report for the two year duration the participant would be eligible and do not remove any approved
participant for any reason until their two year period has expired.
Cancelled applications need to be submitted to the Division of Conservation with a written explanation as to why ASAP.
Use the cancellation form in the workbook. You should still complete the form if the project is cancelled by the district for failure to no response.
Multiple cancellation requests can be made on the same cancelation request form found in your state cost share workbook
Attach a letter or email from the landowner requesting the cancelation when possible
Modifications should be submitted as soon as the original approved steps are not possible, but can be submitted at the end of a contract for things like implementing more units then the
original estimate. The Modification Request form is in the state cost share Excel workbook. Please include county name, month and year at the top. Provide the full practice ID number,
participant name, reason for the modification and then include your modification paperwork w/ tech notes.
For example, if the landowner applied for 700 feet of fence but needed 1000 feet of fence, that is a modification to be submitted with your payment request.
If the landowner applied for fence and a heavy use area, but no longer wants to implement the heavy use area, the application needs to be modified and re-ranked. If without the heavy use
area the application would have ranked too low to have been approved, the modification will be rejected. The landowner can either choose to implement the contract as originally approved or
cancel the contract.
Modifications need to be voted on and approved by the board.
Cost overrun request forms, found in your state cost share workbook are to be used when the landowner exceeds the original approved estimate for their project.
Landowners will be reimbursed for 75% of their ACTUAL receipts up to the maximum amount allowed for their approved practice. Using the cost overrun form assists the Division of Conservation
keep an accurate record of the costs involved in implementing practices and can assist us in adjusting our price lists when needed.
Cost overrun requests are required to keep an accurate financial record
All Cost overruns need to be voted on and approved by the board.
Extension request forms, found in your state cost share workbook are to be used when a participant requires more time to complete their approved practice, please submit the extension request
prior to the end of their first year scheduled completion date, a second extension request can be made prior to the end of the scheduled completion date of their first extension.
Please include a letter or email from the participant for all extension requests expressing their desire to request an extension and an explanation as to why they could ot get their practice complete
in the time granted
Multiple extension requests can be made on the extension request form found in your cost share workbook and attaching all the letter from the participants in the same email
When in doubt you should reach out to your field rep.

## COST SHARE REPORT
STATE COST SHARE MONTHLY STATUS REPORT
CONSERVATION DISTRICT |  |  |  | Month/Year |  | Report should reflect for month listed
FULL APPLICATON ID | FULL APPLICANT NAME | PRACTICE CATEGORY | ORIGINAL AMOUNT APPROVED | OVERRUN AMOUNT APPROVED | AMOUNT PAID TO THE DISTRICT | AMOUNT PAID TO THE APPLICANT | CHECK NUMBER | AMOUNT OF UNOBLIGATED FUNDS IN DISTRICT ACCOUNT | PRACTICE STATUS | EXTENSION
20xx-xxx-xxxxx | AS IT APPEARS ON THE APPLICATION | i.e. CROPLAND | $x,xxx.xx | $x,xxx.xx | $x,xxx.xx | $x,xxx.xx | xxxx | $x,xxx.xx | COMPLETE | xx/xx/20xx
2025 State Cost Share Practices
2026 State Cost Share Practices
TOTALS: |  |  | 0 | 0 | 0 | 0 |  | 0

## EXTENSION REQ.
STATE COST SHARE EXTENSION REQUEST | [5 empty] | Revised: October 2024
CONSERVATION DISTRICT |  | DATE
FULL APPLICATION ID | APPLICANT NAME | PRACTICE CATEGORY | ORIGINAL COST ESTIMATE APPROVED | ORIGINAL COMPLETION DATE | REQUESTED EXTENSION COMPLETION DATE | REASON PRACTICE COULD NOT BE COMPLETED IN ORIGINAL TIME FRAME
20xx-xxx-xxxxx | AS APPEARS ON APPLICATION | i.e. LIVESTOCK-PASTURELAND | $x,xxx.xx | xx/xx/xxxx | xx/xx/xxxx | e.g. EXTREMELY WET WEATHER
Please include the letters from the participants requesting the extension in the same email if possible and preferably in pdf file format. Make sure the name is legible and includes the full practice ID number on each letter.

## EXTENSION INFO
Extension requests letters need to be written by the landowner. When requesting extension requests for multiple participants
please include all the names on the state cost share extension request form found in the state cost share Excel workbook. Please
include the county name, month and year in the spaces provided at the top of the form. Make sure the full practice ID number
(i.e. 20xx-xxx-12345) name of participant, the type of practice (i.e. cropland, livestock-pastureland) and the reason for the extension
request. Please include the letters from the participants requesting the extension in the same email if possible and preferably in pdf file
format. Make sure the name is legible and includes the full practice ID number on each letter.
All extension requests need to be sent in to the Division of Conservation (conservation@ky.gov) using the paperwork in the most recent SCS workbook.
Update the landowner on approval of extension with new completion due date
If the landowner will need a second extension, refer to the steps above.
All schedules for extensions and deadlines should be tracked by the conservation district.
All applications must be completed within 2 years. There are no extensions approved beyond 2 years.

## CANCELLATION REQ.
STATE COST SHARE CANCELLATION REQUEST | [5 empty] | Revised: October 2024
CONSERVATION DISTRICT |  | DATE
FULL APPLICATION ID | APPLICANT NAME | PRACTICE CATEGORY | ORIGINAL COST ESTIMATE APPROVED | ORIGINAL COMPLETION DATE | REQUESTED CANCELLATION DATE | REASON FOR CANCELLATION OF THE PRACTICE
20xx-xxx-xxxxx | AS APPEARS ON APPLICATION | i.e. LIVESTOCK-PASTURELAND | $x,xxx.xx | xx/xx/xxxx | xx/xx/xxxx | i.e. FAILED TO COMPLETE IN THE TIME ALLOTTED
If the landowner has requested the cancellation, please include the letter from the participant requesting the cancellation in the same email and preferably in pdf file format. Make sure the name is legible and include the full practice ID number on each letter. If the district cancels the project due to no response, please include a copy of the meeting minutes with the form.

## CANCELLATION INFO
If the 1 year mark has passed and the conservation district cannot reach the landowner after multiple attempts, the conservation district can vote to cancel
the contract due to no contact. This should be noted in the meeting minutes.
If the board votes to cancel a contract, the conservation district needs to inform the Division of Conservation by using the cancellation form in the SCS Excel
workbook found on the Division of Conservation website and sent to conservation@ky.gov. When requesting cancellation requests for multiple participant
please include all the names on the state cost share cancellation request form. Please include the county name, month and year in the spaces provided at the
top of the form. Make sure the full practice ID number (i.e. 20xx-xxx-12345) name of participant, the type of practice (i.e. cropland, livestock-pastureland) and
the reason for the cancellation request. If the landowner has requested the cancellation, please include the letters from the participant requesting the
cancellation in the same email and preferably in pdf file format. Make sure the name is legible and include the full practice ID number on each letter. If the
district cancels the project due to no response, please include a copy of the meeting minutes with the form.

## OVERRUN REQ.
STATE COST SHARE OVERRUN REQUEST | [5 empty] | Revised: October 2024
CONSERVATION DISTRICT |  | DATE
FULL APPLICATION ID | APPLICANT NAME | PRACTICE CATEGORY | ORIGINAL or Modification COST ESTIMATE APPROVED | ORIGINAL COMPLETION DATE | AMOUNT OF OVERRUN FUNDS REQUESTED | DESCRIPTION OF WHY THERE IS AN OVERRUN
20xx-xxx-xxxxx | AS APPEARS ON APPLICATION | i.e. LIVESTOCK-PASTURELAND | $x,xxx.xx | xx/xx/xxxx | $x,xxx.xx | i.e. EXCESSIVE ROCK REMOVAL ABOVE THE ESTIMATE
Please include all receipts with the Overrun Request. Include a tally sheet listing all receipts scanned with total.

## OVERRUN INFO
Cost overrun request forms, found in your state cost share workbook are to be used when the landowner exceeds the original approved
estimate for their project.
Landowners will be reimbursed for 75% of their ACTUAL receipts up to the maximum amount allowed for their approved practice. Using the
cost overrun form assists the Division of Conservation keep an accurate record of the costs involved in implementing practices and can assist
us in adjusting our price lists when needed.
Cost overrun requests are required to keep an accurate financial record
All Cost overruns need to be voted on and approved by the board.

## MODIFICATION REQ.
STATE COST SHARE CONTRACT MODIFICATION FORM
| County: |  |  | Month: |  |  | Year:
Full Contract ID#: |  |  |  | Applicant Name:
Original Practices Approved |  |  |  | Practice Category:
Practice Name |  | Full Practice Code |  | # Units | Unit Type | Cost Share Amount |  | Action
Total Original CS:
All Practices Requested |  |  |  | Note: Practice Category cannot not change.
Practice Name |  | Full Practice Code |  | # Units | Unit Type | Cost Share Amount
|  |  | Total Revised CS Requested: |  |  | 0
Description of Modification: Include reason for change, resource protection effect from original, etc.
Conservation District Signature:
Date
Applicant Signature:
Date

## MODIFICATION INFO
Instructions: Please fill out all fields as labeled. For Contract ID#, please include identification number as it appears on the approval list with funding year -
county code - number (example: 2018-005-12345). In the table for Original Practices Approved, please list the practices that were approved for funding in
the original contract as shown on the application. In the "Action" box, please indicate if each practice will remain intact (Keep), change units (Edit Units),
or be removed (Remove). In the table for New Practices Requested, please list all practices/edits that will be incorporated in the new application in total.
This should reflect all practices for which funding is being requested, even if no change was made to that particular practice from the original application:
i.e. it will be a snapshot of the entire new contract after modification.
NOTE: Be sure to include the entire SCS practice code under the Practice Code column, including the letter with the NRCS practice code number.
For example: an exclusion fence should be 382A, not solely 382.
Modifications should be submitted as soon as the original approved steps are not possible, but can be submitted at the end of a contract for things like
implementing more units then the original estimate. The Modification Request form is in the state cost share Excel workbook. Please include county name,
month and year at the top. Provide the full practice ID number, participant name, reason for the modification and then include your modification paperwork
with tech notes.
For example, if the landowner applied for 700 feet of fence but needed 1000 feet of fence, that is a modification to be submitted with your payment request.
If the landowner applied for fence and a heavy use area, but no longer wants to implement the heavy use area, the application needs to be modified and
re-ranked. If without the heavy use area the application would have ranked too low to have been approved, the modification will be rejected. The landowner
can either choose to implement the contract as originally approved or cancel the contract.
Modifications need to be voted on and approved by the board.